## GanttChart
VIII Semester Major Project (2015-2016)
R.V.College of Engineering, Bangalore
| Project Title: | Oauth Server for secure Business Services
| Team Members: | Chirag R C N Sudeep Pareekshith K J
| Today's Date: | 2016-02-16 | 2016-02-16 | (vertical red line)
[42] | Start Date: | 2016-01-04 | 2016-01-04 | time axis 2016-01-04 to 2016-12-02
WBS | Tasks | Project member | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2016-01-04: 2016-01-04; 2016-01-11: 2016-01-11; 2016-01-18: 2016-01-18; 2016-01-25: 2016-01-25; 2016-02-01: 2016-02-01; 2016-02-08: 2016-02-08; 2016-02-15: 2016-02-15; 2016-02-22: 2016-02-22; 2016-02-29: 2016-02-29; 2016-03-07: 2016-03-07; 2016-03-14: 2016-03-14; 2016-03-21: 2016-03-21; 2016-03-28: 2016-03-28; 2016-04-04: 2016-04-04; 2016-04-11: 2016-04-11; 2016-04-18: 2016-04-18; 2016-04-25: 2016-04-25; 2016-05-02: 2016-05-02; 2016-05-09: 2016-05-09; 2016-05-16: 2016-05-16; 2016-05-23: 2016-05-23; 2016-05-30: 2016-05-30; 2016-06-06: 2016-06-06; 2016-06-13: 2016-06-13; 2016-06-20: 2016-06-20; 2016-06-27: 2016-06-27; 2016-07-04: 2016-07-04; 2016-07-11: 2016-07-11; 2016-07-18: 2016-07-18; 2016-07-25: 2016-07-25; 2016-08-01: 2016-08-01; 2016-08-08: 2016-08-08; 2016-08-15: 2016-08-15; 2016-08-22: 2016-08-22; 2016-08-29: 2016-08-29; 2016-09-05: 2016-09-05; 2016-09-12: 2016-09-12; 2016-09-19: 2016-09-19; 2016-09-26: 2016-09-26; 2016-10-03: 2016-10-03; 2016-10-10: 2016-10-10; 2016-10-17: 2016-10-17; 2016-10-24: 2016-10-24; 2016-10-31: 2016-10-31; 2016-11-07: 2016-11-07; 2016-11-14: 2016-11-14; 2016-11-21: 2016-11-21; 2016-11-28: 2016-11-28
2 | Phase 1 |  | 2016-01-04 | 2016-01-19 | 15 | 100% | 15 | 15 | 0
1.1 | Objectives |  | 2016-01-04 | 2016-01-10 | 6 | 100% | 6 | 6 | 0
1.2 | Methodology |  | 2016-01-10 | 2016-01-19 | 9 | 100% | 9 | 9 | 0
2 | Phase 2 |  | 2016-01-19 | 2016-02-16 | 28 | 100% | 28 | 28 | 0
2.1 | Complete Methodology |  | 2016-01-19 | 2016-02-04 | 16 | 100% | 16 | 16 | 0
2.2 | Literature Review |  | 2016-02-04 | 2016-02-16 | 12 | 100% | 12 | 12 | 0
3 | Phase 3 |  | 2016-02-16 | 2016-03-18 | 31 | 0% | 31 | 0 | 31
3.1 | High level design |  | 2016-02-04 | 2016-02-09 | 5 | 100% | 5 | 5 | 0
3.2 | Low Level Design |  |  |  | 0 | 0% | 0 | 0 | 0
4 | Full Implementation |  |  |  | 0 | 0% | 0 | 0 | 0
4.1 | Routing |  | 2016-02-09 | 2016-02-20 | 11 | 70% | 11 | 7 | 4
4.2 | Authentication |  |  |  | 0 | 0% | 0 | 0 | 0
4.3 | Throttling |  |  |  | 0 | 0% | 0 | 0 | 0
4.4 | Authorization
5 | Testing |  | 2016-03-18 | 2016-04-12 | 25 | 0% | 25 | 0 | 25
5.1 | Unit Testing |  |  |  | 0 | 0% | 0 | 0 | 0
5.2 | Integration Testing |  |  |  | 0 | 0% | 0 | 0 | 0
6 | Deployment
7 | Result and anlaysis |  |  |  | 0 | 0% | 0 | 0 | 0
8 | Conclusion and Future work |  |  |  | 0 | 0% | 0 | 0 | 0
9 | Report Writing |  |  |  | 0 | 0% | 0 | 0 | 0
Note on J1: COMMERCIAL USE LICENSE This spreadsheet has been commercially licensed from Vertex42 LLC (the "Licensor"). If you have received this file from anyone other than the Licensor or the designated Licensee, as allowed in the commercial license agreement, please destroy all copies of this spreadsheet in your possession and report the violation to Vertex42.com. See the following page page for details about the commercial use license: http://www.vertex42.com/licensing/EULA_commercialuse.html Restrictions (a) You may not distribute, sell, rent, lease, sublicense, or otherwise transfer rights to, any portion of this Software. The Licensee may only give a copy of this spreadsheet to an individual client if the client has also purchased a commercial license of the Software. (b) You may not remove, alter, or hide the original logo, trademarks, copyright, hyperlinks, disclaimers, terms of use, or other proprietary notices. (c) You may not place the Software onto a server or computer so that it is accessible via a public network, such as the internet. (d) You may not merge the Software into another program or create any derivative works of the Software or its documentation. (e) You may not copy the Documentation or copy the Software except as indicated in the Commercial Use Grant. (f) You may not reverse engineer, decompile, or disassemble the Software. No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Somes states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.
Note on A12: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on D12: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on E12: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on F12: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. For the main tasks, you can calculate the duration by finding the maximum End date of the sub tasks and subtracting the earliest start date. For example: F11=MAX(E12:E15)-D11
Note on G12: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). For the main tasks, you can use a weighted average of the sub tasks by adding the formula: G11=SUMPRODUCT(F12:F15,G12:G15)/SUM(F12:F15) Note: If you insert rows, make sure that the calculation is updated correctly.
Note on H12: Working Days Counts only Mon-Fri, using the NETWORKDAYS() formula. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached. Note: If the start date is later changed, the number of working days may also change.
Note on I12: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J12: Calendar Days Remaining This column is calculated by subtracted the Days Complete from the Duration.